## Gantt Chart w % Complete
Project Schedule
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Design and Engineering
| Control Table | 2019-10-09 | 9 | 2019-10-10 | 1 | 1 | 0 | Khaliq | 100%
| Architecture of the System | 2019-10-10 | 10 | 2019-10-11 | 1 | 1 | 0 | Khaliq | 100%
| Architecture of the Software | 2019-10-14 | 14 | 2019-10-15 | 1 | 1 | 0 | Khaliq | 100%
| Interface Agreement | 2019-10-15 | 15 | 2019-10-17 | 2 | 2 | 0 | all members | 100%
| Verification | 2019-10-18 | 18 | 2019-10-28 | 10 | 10 | 0 | all members | 100%
Development of Software Modules
| Architecture of Module | 2019-10-29 | 29 | 2019-10-31 | 2 | 0.1 | 1.9 | Imran, Nihad, Khaliq | 5%
| Development of Module | 2019-11-01 | 1 | 2019-11-14 | 13 | 0 | 13 | Imran, Nihad, Khaliq | 0%
| Testing of Module | 2019-11-14 | 14 | 2019-11-18 | 4 | 0 | 4 | Afrasiyab | 0%
| Verification | 2019-11-18 | 18 | 2019-11-19 | 1 | 0 | 1 | all members | 0%
Integration
| Integration | 2019-11-19 | 19 | 2019-11-26 | 7 | 0 | 7 | Afrasiyab | 0%
| Testing of Integrated Modules | 2019-11-26 | 26 | 2019-11-29 | 3 | 0 | 3 | Afrasiyab | 0%
| Verification | 2019-11-30 | 30 | 2019-12-05 | 5 | 0 | 5 | all members | 0%
Presentation of Project
| Final stage | 2019-12-06 | 6 | 2019-12-12 | 6 | 0 | 6 | Imran | 0%